## Milestones
MyMouNa v1.0 (Android Milestones)
Global Milestones
Id | Ends | Milestone | Assigned To | % | Detail | Description
| 2018-02-09 | Project Start | Client | 100% |  | Platform aims to Promote and generate revenue from Music from Guinea using a Mobile Application. • Users listen to Audio and Video tracks from YouTube • Users Chat in Groups • Users discuss/share Content found in the App • Users Buy Content released by Artists • Artits Manage their Audio/Video Content • Admins Manage Ads
1 | 2018-03-05 | Build the App's Music/Video features | Contractor | 100% | Milestone #1
2 | 2018-03-30 | Build Content Editor's Initial features. Social Sign-On. | Contractor | 0% | Milestone #2
4 | 2018-04-16 | Build the App's Chat features | Contractor | 0% | Milestone #3
5 | 2018-04-30 | Build the App's Blog features | Contractor | 0% | Milestone #4
6 | 2018-06-04 | Build Purchasing features for Music/Events Booking | Contractor | 0% | Milestone #5
7 | 2018-06-19 | Build the App's Advertising features | Contractor | 0% | Milestone #6
| 2018-06-20 | Project End | Client | 28.57%

## Sprints
MyMouNa v1.0 (Android Sprints)
Software Development Milestones
Id | Ends | Milestone | Assigned To | Position | Baseline
| 2018-02-09 | Project Start | Client | 20 | 0
0
| 2018-02-10 | Sprint#1 Starts | Client | 15 | 0
1.1 | 2018-02-12 | Skeleton (theming, menus, pages, flows, login) | Contractor | -10 | 0
1.2 | 2018-02-16 | Songs UI/UX (artists, albums, audios, minified/magnified player) | Contractor | -7 | 0
1.3 | 2018-02-23 | Videos UI/UX (player, YouTube ready) | Contractor | -5 | 0
1.4 | 2018-03-02 | API that Reads/Creates/Edits Songs,Videos | Contractor | 5 | 0
1.5 | 2018-03-04 | Misc. features (multilanguage, bug tracking) | Contractor | 10 | 0
| 2018-03-05 | Milestone #1 Ends - Release & Brainstorm | Client | 15 | 0
0
| 2018-03-13 | Sprint#2 Starts | Client | 15 | 0
2.1 | 2018-03-16 | Sign-in with Facebook or Google+ | Contractor | 10 | 0
2.2 | 2018-03-19 | Web Content Editor for Milestone #1 | Contractor | -5 | 0
2.3 | 2018-03-26 | Upgrade, Segregated access/settings for Artists, Admins | Contractor | 10 | 0
2.4 | 2018-03-30 | Mobile Contents Editor (intial) - Songs/Videos, Artists/Albums | Contractor | -10 | 0
| 2018-03-30 | Milestone #2 reached - Release & Brainstorm | Client | 15 | 0
0
| 2018-04-01 | Sprint#3 Starts | Client | 15 | 0
3.1 | 2018-04-04 | IM Chat Core UI/UX (contacts, rooms, conversations, etc.) | Contractor | -10 | 0
3.2 |  | API for Realtime Chat/Rooms | Contractor | 5 | 0
3.3 |  | Share Multimedia Content on IM | Contractor | 10 | 0
| 2018-04-16 | Milestone #3 reached - Release & Brainstorm | Client | 15 | 0
0
| 2018-04-17 | Sprint#4 Starts | Client | 15 | 0
4.1 |  | Artists Blog UI/UX (directory, headlines, master/detail views) | Contractor | -10 | Chat Core UI/UX (contacts, rooms, conversations, etc.)
4.2 |  | API for Blogging | Contractor | 10 | API for Realtime Chat/Rooms
4.3 |  | Share Blog Article on Social Networks | Contractor | 10 | Chat Multimedia Content Sharing
| 2018-04-30 | Milestone #4 reached - Release & Brainstorm | Client | 15 | Milestone #3 reached - Release & Brainstorm
0
| 2018-05-01 | Sprint#5 Starts | Client | 15
5.1 | 2018-05-07 | API for Downloading Purchased Music (GCS & OMoney) | Contractor | 10 | 0
5.2 | 2018-05-21 | API to Book Events (GCS and OMoney) | Contractor | 5 | 0
5.3 | 2018-05-28 | Music Download UI/UX | Contractor | -10 | 0
5.4 | 2018-05-28 | Events Booking UI/UX | Contractor | -5 | 0
5.5 | 2018-05-31 | Content Editor (upgrade) - Downloads/Events, with Purchase history | Contractor | -10 | 0
| 2018-06-04 | Milestone #5 reached - Release & Brainstorm | Client | 15 | 0
0
| 2018-06-05 | Sprint#6 Starts | Client | 15 | 0
6.1 | 2018-06-11 | API for Reading/Creating/Editing Ads | Contractor | 10 | 0
6.2 | 2018-06-11 | Ads UI/UX | Contractor | -10 | 0
6.3 | 2018-06-18 | Content Editor (upgrade) - Ads | Contractor | -5 | 0
6.4 | 2018-06-18 | Build the App for Production | Contractor | 10 | 0
6.5 | 2018-06-19 | Milestone #6 reached - Release & Brainstorm | Contractor | 15 | 0
6.6 | 2018-06-19 | Final release on Playstore | Contractor | -15 | 0
| 2018-06-20 | Project End | Client | 20 | 0